## Sheet1
Group Member | Task | Expected Completion Date | Actual Completion Date | Notes
All group members | Discuss what type of navigation system we will be implementing and go into full detail on how we will do the implementation | 2016-04-27 |  | Created a google document that documented the description of our naviagtion system
All group members | Complete Phase 4 of the project | 2016-04-29 |  | Proofread all information that we came up with for this phase to ensure that we have met the criteria for Phase 4 Requirements before submitting Phase 4
All group members | Create a grid layout | 2016-04-29 |  | This layout will show how we want all of the information to be displayed on our website
All group members | Create a PowerPoint presentation for our project (Phase 5) | 2016-04-30 |  | Each group member will work on 1-2 slides describing our process in completing this project
Shannon, Brianna | Complete the coding of our website | 2016-04-29 |  | Complete the coding for our website by writing, compiling and running the code, and fixing any errors that may arise
Cassandra | Submit Phase 4 | 2016-04-29 |  | Submitting Phase 4 to Github and Moodle
Cassandra | Submit Phase 5 | 2016-04-30 |  | Submitting Phase 5 to Github and Moodle